## 27-7-15
Issues 27 July 2015 | Status | Comments | Status- 30 July
We’ve reviewed the MSJ site Live code at: http://myspeakingjourney.com:4000/learningstream and have made notes of what needs to be fixed or worked on and as well a few things that relate to our call. | Done - please check updated site at http://myspeakingjourney.com | Was working earlier today, stopped working as did port 4000. Would really like to see this resolved and fully working. | Done - please check updated site at http://myspeakingjourney.com
General
The homepage of MSJ should be the LS page displaying POKs | User can view LS when he will be login without login he cant see LS | This is not how it is to work. Homepage of MSJ is the LS and it is viewable by all without Login or Account. Login and account are only needed when a user is to Share or Follow the LS. | Done
Content Alignment - Content is not appearing in the same place. Please compare where the content starts in relation to the left edge of the book on the following pages:MSJ >> About MSJ >> Feedback MSJ >> Contact Learning Stream >> Home Learning Stream >> Share Your Knowledge | Done - please check | Site is down, can't check. When I checked this earlier I did not see this working properly. For example, About and Features and Planned Features were not lining up properly. Will need to review again when site is back up. | Done
There is no consistency in where the content starts compared to the left edge and there needs to be. All pages need to have the content start in the same spot. Please have them all aling with MSJ >>About. MSJ >>About is the content position we like best and need everything else to align to this. | Done - please check | Same point as above. | Done
Please explain how we can get setup on GitHub (what to download and how to setup) and also use it to modify an About page and to have those pages updated on the server. | In process
Please explain how we can connect Mongo DB and manage collections (tables ), records ( documents ). If you can explain how to clear a collection and a document that would be greatly appreciated. | In process
Sign In and Sign Up
Facebook login is not working yet. The message is now different and is as follows:Given URL is not allowed by the Application configuration: One or more of the given URLs is not allowed by the App's settings. It must match the Website URL or Canvas URL, or the domain must be a subdomain of one of the App's domains. | We have checked that facebook login is working now for non developer accounts. Can you please check login with non developer account? | Site down. | Done
LinkedIn login is not working. We are getting an error as follows: invalidredirect_uri. This value must match a URL registered with the All Applications can be found in your settings | Please give us a screen shot which shows the callback url for linked in and twitter? So that we can check the callback urls and suggest the updated one | Screenshot provided, url was missing, sorry, we thought we had done this. | Done
On the Sign Up page, when signing up by Email, message should be: Congratulations! (not Congratulation, needs an ‘s’). Your registration was successful! Please display this message for 3 seconds and then automatically log the user in rather than having them click on a link that goes back to the Sign In page. | Done | Site down, will check. | Done
Feedback and Contact Forms
MSJ >> Feedback - the heading on this page which reads ‘Feedback’ is not the same style as the heading on MSJ >>About, see word ‘About’. For clarity, ‘Feedback’ heading does not look like ‘About’. Please make Feedback look the same way as MSJ >>About. Similarly, make headings on MSJ >> Contact, Learning Stream >> Feedback also match the heading style on MSJ >>About. | Done | Site down. | Done
Please see new Contact Form attached. Contact form now has two sides and uses the divided book page that is used on Sign In and Sign Up. Left side has a phone number and displays our email address. Right side has contact form. | Done | Site down. | Done
Learning Stream
Domain name just displays the root of the domain, not directories. We want:( locomotivejs.org ) not ( locomotivejs.org/guide/views/ ) | Done |  | Done
MSJ and About Pages
Please create two new sub-navigation elements named: ‘Features and Planned Features’ and ‘Guiding Principles’. | Done | Saw this earlier, need to check again when site back up. | Done
The sub-navigation on MSJ will be: About,Features and Planned Features,Guiding Principles, Feedback,Contact | Done | Site down, need to check. | Done
The content on the About page will changed to the following and two links will be added to the last line as follows: My Speaking Journey is the first and only online network dedicated to public speaking. Our mission is to help you become the best the speaker you can be and make your public speaking journey exciting and fun. We help you connect, share and learn from other public speakers. Our goal is to help you become a better speaker. Being the best speaker you can be, is a journey, not a destination. It involves continually learning and finding new ways of doing things that make you better than your previous speaking self. We launched in August 2015! We’ve started with the Learning Stream and we’ll release planned features in the coming months and we’ll stay true to a set of guiding principles. | Done | Looked good but need to check again. | Done
For Features and Planned Features, please use the section on the About page with that info. For Guiding Principles, please use the section on the About page. | Done |  | Done
Design
Tabs are moving when clicked on. For example, click on MSJ tab, then click on LS and the click on MSJ tab. You will see the MSJ tab moving position. We realize you are still making changes to design and responsiveness etc. but we will pass this comment on now. | Done | Site down, need to check. | Done

## 31-7-15
Sl.No. | Issues Open | Status | Comments | Status- 30 July
1 | Install Mail Server Paid gmail account for :- > brian@myspeakingjourney.com > marushka@myspeakingjourney.com > msj@myspeakingjourney.com (for all services of MSJ website) | Open |  | Remaining
2 | Responsive a. Responsiveness on websites (design still looks zoomed in) b. Responsiveness on mobile devices | Open |  | Remaining
3 | Follow us on Learning Stream Follow us leads to the Sign-up page but does'nt show the pop-up once the user signs up | Open |  | Remaining
4 | Share on Learning Stream > Share leads to the Sign-up page but does'nt show the pop-up once the user signs up | Open |  | Remaining
5 | Call Back > Call back for Facebook - done > Call back for Twitter - done > Call back for Linkedin - pending email setup with company domain | Open | Will we never be able to login using the facebook developeraccount? | Remaining
6 | More Arrows at the Bottom of Learning Stream "More" needs to be in itallics and after arrow is clicked, arrow turns blue. There is no hover effect, and there is no blue box. You have the blue to be used already. | Open |  | Done
7 | About About the Learning Stream heading does not appear despite it being marked off as completed. This was done incorrectly. Tab headings are as follows: > MSJ Tab >> About >> Heading is: About > LS Tab >> About Learning Stream >> Heading is: About the Learning Stream | Open |  | Done
8 | Home Page is Learning Stream This has been completed and it is working perfectly well | Closed |  | Done
| URL validation on Learning Stream The domain still needs to be a clickable link. When a domain was submitted as: www.domain.com On the KA page, it was not clickable and did not go to domain.com In summary, the user can enter domain.com or www.domain.com but it still needs to be a valid url on the KA page and on the LS page. The description field, can be submitted without an value. However, if we type in a character or two, the message comes up about 150 characters. We don't know where this came from but we want nothing about minimum characters. This was not in the spec about 150 characters, please remove. | Open |  | Done
9 | Implement Fogot Password Will do a final check! | Closed |  | Done
10 | Terms and Conditions > This will be worked on and sent to be added >Blue check mark in the psd design is not being displayed on Terms and Conditions, instead it is a question mark | Open |  | Remaining
11 | Welcome Tab When a user has logged, Welcome is gone and the username instead is displayed there. This is currently not happening | Open |  | Done-welcome is coming with username
12 | Admin When logged in as Admin, under the LS tab, only Knowledge Approval is appearing. All LS sub-navigation should be shown in addition to Knowledge Approval for the admin. | Open | Regarding Admin LS tab - Please let us know we have to show only sub navigation or sub navigation with functionality, currently we are showing Knowledge approval as per the initial scope of project if we going to implement the sub navigation's of Admin LS similar to user LS then it will increase the time and estimation of project. | Remaining
| Admin - Tracking Request for additional colum for tracking | Open |  | Remaining
13 | Main Tabs When main tab when you are already in the tab links to the leftmost sub-navigation element. For example, I am in in MSJ tab and on the sub-navigation element Contact but I click on MSJ tab, this will bring up the MSJ Home tab. Similarly, LS tab will bring up LS Home when it is clicked on when LS is clicked on in any sub-navigation element. Similarly, when User/Welcome tab is clicked on when in User sub-navigation, it will bring up Change Password. | Open |  | Remaining
14 | Sign In > Are users able to sign in through both email address and Username? > The label inside should read - "Email Address or Username" currently it only reads "Username" | Open |  | Done
15 | Sign Up > The label inside should read - "Email Address or Username" currently it only reads "Username" > The left hand side of the Sign Up page is missing a link for Sign In. | Open |  | Remaining